## Sheet1
Activity | Team Member(s) | Week
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
1. Initiation and Planning phase
1.1 Project Proposal
Design Project Proposal | Brett | bar: Week 1
2. Execution
2.1 Pump Controller
Create Hardware Design | Jase | bar: Week 2 to Week 4
Manufacture Parts Needed | Jase | bar: Week 4 to Week 6
Develop a network connection | Kristian | bar: Week 7 to Week 9
Create interactive software application | Brett | bar: Week 8 to Week 9
Define user/admin privileges | Brett | bar: Week 9 to Week 10
Test hardware parts | All | bar: Week 11 to Week 12
2.2 Mobile Application
Set up app layout | Brett | bar: Week 3 to Week 6
Establish Connection with Hardware | Kristian | bar: Week 7 to Week 8
Establish Connection with Server | Kristian | bar: Week 7 to Week 8
Test app with prototype | All | bar: Week 9 to Week 10
2.3 Database
Design database schema | Brett | bar: Week 2 to Week 4
Set up database | Brett | bar: Week 5 to Week 6
Establish Connection with Server | Brett | bar: Week 7 to Week 8
User Priviledges | Brett | bar: Week 7 to Week 9
2.4 Website
2.4.2 Front End
Receive admin requirements | Kristian | bar: Week 2 to Week 4
Create Homepage | Kristian | bar: Week 4 to Week 6
Create Admin Login Page | Kristian | bar: Week 7 to Week 9
Establish Connection with Server | Kristian | bar: Week 9 to Week 10
Map local pump controllers to station | Brett | bar: Week 11 to Week 12
2.4.3 Back End
Design API | Jase | bar: Week 2 to Week 3
Develop simple backend framework | Jase | bar: Week 3 to Week 6
Establish database connection | Brett | bar: Week 7 to Week 8
Create points for connectivity | Jase | bar: Week 8 to Week 11
3 Monitoring and Controlling phase
3.1 Code Tests
3.1.1 Unit Tests
Test hardware | Jase | bar: Week 6 to Week 10
Test website | Kristian | bar: Week 6 to Week 10
Test mobile app | Kristian | bar: Week 8 to Week 10
Test API | Jase | bar: Week 8 to Week 10
Test system | All | bar: Week 8 to Week 12
3.1.2 Integration Tests
Hardware to Server | Jase | bar: Week 8 to Week 12
Front-End to Back-End | Kristian | bar: Week 8 to Week 12
Back-End to Database | Brett | bar: Week 8 to Week 12
3.1.3 User Tests
Small group user testing | All | bar: Week 11 to Week 12
3.2 Documentation
3.1.1 Progress Reports
Create Progress Report | All | bar: Week 2 to Week 12
3.1.2 Daily SCRUM meeting
Record Notes | All | bar: Week 2 to Week 12
3.1.2 Weekly Meeting Notes
Update Meeting Notes | All | bar: Week 2 to Week 12
4. Closing
4.1 Closing Documentation
4.1.1 Project Reflection
Create Project Reflection | Brett | bar: Week 13
4.1.2 Compression Plan
Create Compression Plan | Jase | bar: Week 13
4.1.3 Potential Optimization Plans
Create Optimization Plans | Kristian | bar: Week 13