## Sheet1
Activity | Week
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
1. Initiation and Planning phase
1.1 Project Proposal
Design Project Proposal
2. Execution
2.1 Pump Controller
Create Hardware Design
Manufacture Parts Needed
Develop a network connection
Create interactive software application
Define user/admin privileges
Test hardware parts
2.2 Mobile Application
Set up app layout
Establish Connection with Hardware
Establish Connection with Server
Test app with prototype
2.3 Database
Design database schema
Set up database
Establish Connection with Server
User Priviledges
2.4 Website
2.4.2 Front End
Receive admin requirements
Create Homepage
Create Admin Login Page
Establish Connection with Server
Map local pump controllers to station
2.4.3 Back End
Design API
Develop simple backend framework
Establish database connection
Create points for connectivity
3 Monitoring and Controlling phase
3.1 Code Tests
3.1.1 Unit Tests
Test hardware
Test website
Test mobile app
Test API
Test system
3.1.2 Integration Tests
Hardware to Server
Front-End to Back-End
Back-End to Database
3.1.3 User Tests
Small group user testing
3.2 Documentation
3.1.1 Progress Reports
Create Progress Report
3.1.2 Daily SCRUM meeting
Record Notes
3.1.2 Weekly Meeting Notes
Update Meeting Notes
4. Closing
4.1 Closing Documentation
4.1.1 Project Reflection
Create Project Reflection
4.1.2 Compression Plan
Create Compression Plan
4.1.3 Potential Optimization Plans
Create Optimization Plans